## Sheet1
Project Schedule
| 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31
Phase 1: Prepration
Literature Review | bar: 2020-06-01 to 2020-06-22
Review Existing Visualization Libraries | bar: 2020-06-08 to 2020-06-22
Learn Functional Programming Techniques | bar: 2020-06-08 to 2020-06-22
Implement Basic Library Structure | bar: 2020-06-08 to 2020-06-22
Write Project Plan | bar: 2020-06-15 to 2020-06-22
Phase 2: Execution
Design Advanced Components of Library | bar: 2020-06-29 to 2020-07-20
Learn Further Library Design Principles | bar: 2020-06-29 to 2020-07-20
Write Summary of Work Done So Far | bar: 2020-07-13 to 2020-07-20
Review Codebase | bar: 2020-07-13 to 2020-07-20
Phase 3: Summary
Test Library | bar: 2020-07-27 to 2020-08-03
Review Summaries | bar: 2020-07-27 to 2020-08-17
Write Independent Research Report | bar: 2020-08-17 to 2020-08-31
On-going
Meet Supervisor
Write Unit Tests | bar: 2020-06-08 to 2020-08-17